## Defect_tracker
Sl No | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | 2025-11-03 | Foreign key constraint fails on sample route references | Sprint 1 | Backend Team | Functional | Validated seed data; added FK checks and clear errors | 2025-11-04 | Closed | Verified successfully
2 | 2025-11-05 | Transaction not rolling back leaves residual rows | Sprint 1 | Backend Team | Algorithmic | Wrapped multi-table insert in transaction; added rollback on error | 2025-11-06 | Closed | No residuals after tests
3 | 2025-11-10 | Search API accepts invalid date and returns 500 | Sprint 2 | Backend Team | UI/validation | Added input schema validation and graceful 400 responses | 2025-11-11 | Closed | Tested and verified
4 | 2025-11-12 | Dynamic pricing not applied in search results | Sprint 2 | Backend Team | Integration | Integrated pricing engine into query pipeline | 2025-11-14 | Closed | Prices reflect demand/time
5 | 2025-11-17 | Concurrent seat booking race condition | Sprint 3 | Backend Team | Logic | Introduced row-level locks and retries; tightened isolation | 2025-11-19 | Closed | Verified under load
6 | 2025-11-18 | Rare duplicate PNR generated under load | Sprint 3 | Backend Team | Functional | Added uniqueness retry on collision and DB unique index | 2025-11-20 | Closed | No collisions in soak test
7 | 2025-11-25 | Seat map shows seat available while backend holds it | Sprint 4 | Frontend Team | UI | Hooked UI to hold events and added refresh timer | 2025-11-26 | Closed | Sync within budget
8 | 2025-11-27 | PDF ticket layout overlaps QR with long names | Sprint 4 | Frontend Team | UI | Added wrapping and layout constraints | 2025-11-28 | Closed | Layout stable